## Test Scenario.
Test Sceanario
| Project Name | Node Master
| Created By | Ashish Dadhich
| Created Date | 2025-04-02
Approval Date
Approval By
| Browser/OS | Chrome, Firefox, Edge/Window10
Test Sceanario Id | Test Scenario | Total Test Case
Ts_01 | Validate the SignUp Page | 20
Ts_02 | Validate the Login Page | 18
Ts_03 | Validate the Home Page | 16
Ts_04 | Validate the Profile Page | 20
Ts_05 | Validate the To-Do Page | 15
Ts_06 | Validate the Write Notes Page | 25
Ts_07 | Validate the Create Notebook Page | 6

## SignUp
Test Cases for SignUp
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS_01 | Functional | Check Signup Page Behavior | TC_01 | User navigates to the Signup Page | Ensure all fields load properly | 1. Open the signup page 2. Check form fields | None | All fields should be visible | All fields should be visible | Pass | Loads Properly
|  |  | TC_02 | Valid inputs are entered | Ensure signup works | 1. Enter valid details 2. Click "Sign Up" | Name:Ashish, Email- ashishdadhiich@gmail.com, Password: Singh@123 | User should be registered and redirected | User should be registered and redirected | Pass | As expected
|  |  | TC_03 | Signup Page is displayed | Ensure required fields are validated | 1. Click "Sign Up" without entering data | None | Error message should appear | Error message should appear | Pass | As expected
|  |  | TC_04 | User is viewing the Signup Page | Ensure email format validation | 1. Enter "ashishdadhiich@gmail.com" as email 2. Click "Sign Up" | email- ashishdadhiich@gmai.com | Error: "Invalid email" | SignUp successfully without error message | Fail | Need to fix
|  |  | TC_05 | Signup interface is visible | Ensure weak passwords are rejected | 1. Enter "123" as password 2. Click "Sign Up" | 123456 | Error: "Password too weak" | no any error message "Password too weak" | Fail | Need to fix
|  |  | TC_06 | Accessing the Signup Page | Ensure confirm password matches | 1. Enter different passwords 2. Click "Sign Up" | Password: Test@123, Confirm: Test@124 | Error: "Passwords do not match" | Error: "Passwords do not match" | Pass | As expected
|  |  | TC_07 | Email address is already registered | Ensure duplicate email is not allowed | 1. Enter an already registered email 2. Click "Sign Up" | Existing email: ashishdadhiich@gmail.com | Error: "Email already registered" | Error: "Email already registered" | Pass | As expected
|  |  | TC_08 | User reaches Signup screen | Ensure "Name"field length validation | 1. Enter 50+ characters in Name field | Long name input | Error: "Max length exceeded" | not showing any error message like "Max length exceeded" | Fail | Need to fix
| Security |  | TC_09 | Signup screen is currently open | Ensure no SQL injection is possible | 1. Enter ' OR '1'='1 in fields 2. Click "Sign Up" | SQL injection query | Input should be sanitized | Input should be sanitized | Pass | As expected
| UI |  | TC_11 | The Signup Page is active | Ensure UI elements are aligned properly | 1. Check button and field placement | None | Proper alignment | Proper alignment | Pass | As expected
|  |  | TC_12 | User opens the Signup Page | Ensure text is readable | 1. Check font size and colors | None | Readable and accessible text | Readable and accessible text | Pass | As expected
| Performance |  | TC_13 | Signup form is on screen | Ensure page loads within 2s | 1. Measure load time using dev tools | None | Page should load in 2s | Page should load in 2s | Pass | As expected
|  |  | TC_14 | User lands on the Signup Page | Ensure system handles large data properly | 1. Enter max character values in each field | Large input data | Form should not crash | Form should not crash | Pass | As expected
| Usability |  | TC_15 | Accessing from a mobile device | Ensure mobile UI is working fine | 1. Open on mobile 2. Check layout | None | Page should be responsive | Page should be responsive | Pass | As expected
|  |  | TC_16 | Navigated to the Signup Page | Ensure error messages are user-friendly | 1. Enter invalid details 2. Click "Sign Up" | Invalid email, weak password | Clear and helpful error messages | Clear and helpful error messages | Pass | As expected
| Compatibility |  | TC_17 | Launched in multiple browsers | Ensure page works across browsers | 1. Open in Chrome, Firefox, Edge | None | Signup should work properly | Signup should work properly | Pass | As expected
|  |  | TC_18 | Viewed across different screen resolutions | Ensure UI is not broken | 1. Resize window 2. Check layout | Samsung Galaxy s8+ | Layout should adjust properly | test overlaps ans button aignment issue | Fail | Need to fix
| Negative Testing |  | TC_19 | User redirected to the Signup interface | Ensure error message appears for empty form | 1. Click "Sign Up" without entering anything | None | Error message should appear | Error message should appear | Pass | As expected
|  |  | TC_20 | Signup screen is currently active | Ensure special characters are not allowed in name | 1. Enter @#$$% in Name field 2. Click "Sign Up" | Invalid special characters | Error message should appear | Error message should not appear | Fail | Need to fix

## Login
Test Cases for SignUp
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS_02 | Functional | Verify Login Page | TC_01 | User is on Login Page | Ensure all fields load properly | 1. Open the login page 2. Check form fields | None | All fields should be visible | All fields should be visible | Pass | As expected
|  |  | TC_02 | User has valid credentials | Ensure login works with correct details | 1. Enter valid email & password 2. Click "Login" | Email- ashishdadhiich@gmail.comPassword: ashish@123 | User should be logged in successfully | User should be logged in successfully | Pass | As expected
|  |  | TC_03 | User is on Login Page | Ensure error messages appear for empty fields | 1. Click "Login" without entering data | None | Error message should appear | Error message should appear | Pass | As expected
|  |  | TC_04 | User is on Login Page | Ensure email validation works correctly | 1. Enter "abc" as email 2. Click "Login" | ashishdadhiich@gmail.com | Error: "Invalid email" | Error: "Invalid email" | Pass | As expected
|  |  | TC_05 | User is on Login Page | Ensure login fails with wrong password | 1. Enter valid email but wrong password 2. Click "Login" | Email: test@example.com, Password: Wrong123 | Error: "Incorrect password" | Error: "Incorrect password" | Pass | As expected
|  |  | TC_06 | User is on Login Page | Ensure login fails for unregistered users | 1. Enter an unregistered email 2. Click "Login" | Email: ashishdadhiich@gmail.com Password: ashish@123 | Error: "User not found" | Error: "User not found" | Pass | As expected
|  |  | TC_07 | User is entering password | Ensure password is hidden when typed | 1. Enter password field 2. Check if password is masked | Test@123 | Password should appear as •••••••• | Password should appear as •••••••• | Pass | As expected
|  |  | TC_08 | User is on Login Page | Ensure "Forgot Password" link works | 1. Click on "Forgot Password" link | None | mouse hover effect should available and Redirected to password recovery page | mouse hover effect are not available | Fail | Add mouse hover effect
|  |  | TC_09 | User is on Login Page | Ensure "Signup" link works | 1. Click on "Signup" link | None | Redirected to Signup page | Redirected to Signup page | Pass | As expected
|  |  | TC_10 | User is logged in | Ensure session expires after inactivity | 1. Login 2. Leave idle for 30 minutes 3. Try performing action | None | User should be logged out automatically | User should not be logged out automatically | Fail | Need to fix
| Security |  | TC_11 | User is on Login Page | Ensure no SQL injection is possible | 1. Enter ' OR '1'='1 in fields 2. Click "Login" | SQL injection query | Input should be sanitized | Input should be sanitized | Pass | As expected
| UI |  | TC_12 | User is on Login Page | Ensure UI elements are aligned properly | 1. Check button and field placement | None | Proper alignment | Proper alignment | Pass | As expected
|  |  | TC_13 | User is on Login Page | Ensure text is readable | 1. Check font size and colors | None | Readable and accessible text | Readable and accessible text | Pass | As expected
| Performance |  | TC_14 | User is on Login Page | Ensure page loads within 2s | 1. Measure load time using dev tools | None | Page should load in 2s | Page should load in 2s | Pass | As expected
|  |  | TC_15 | User is on Login Page | Ensure system handles large data properly | 1. Enter max character values in each field | Large input data | Form should not crash | Form should not crash | Pass | As expected
| Usability |  | TC_16 | User is on Mobile | Ensure mobile UI is working fine | 1. Open on mobile 2. Check layout | None | Page should be responsive | Page should not be responsive, test and buttons are verlapping | Fail | Need to fix
|  |  | TC_17 | User is on Login Page | Ensure error messages are user-friendly | 1. Enter invalid details 2. Click "Login" | Invalid email, wrong password | Clear and helpful error messages | Clear and helpful error messages | Pass | As expected
| Compatibility |  | TC_18 | Open in different browsers | Ensure page works across browsers | 1. Open in Chrome, Firefox, Edge | None | Login should work properly | Login should work properly | Pass | As expected

## Home Page
Test Cases for SignUp
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS_03 | Functional | Verify Home Page | TC_01 | User is logged in | Check if the homepage loads without errors | 1. Open the browser 2. Navigate to the NoteMaster page 3. Check for UI elements | None | Page should load successfully with all elements visible | Page should load successfully with all elements visible | Pass | As expected
|  |  | TC_02 | Page is loaded | Check if clicking "Write Notes" opens the editor | 1. Locate the "Write Notes" button 2. Click the button 3. Check if the editor opens | None | Editor should open | Editor should open | Pass | As expected
|  |  | TC_03 | Page is loaded | Clicking "Create Notebook" should open a modal | 1. Click on "Create Notebook" button 2. Check if a modal appears | None | Notebook creation modal should open | Notebook creation modal should open | Pass | As expected
| UI/UX |  | TC_04 | Page is loaded | Check if all elements are aligned | Visually inspect UI elements | None | Elements should be properly aligned | Elements should be properly aligned | Pass | As expected
| Usability |  | TC_05 | User is logged in | Check if "Hi, Shivendra" and profile icon are visible | Locate the username and profile icon on the top right | None | Profile section should be displayed | Profile section should be displayed | Pass | As expected
| Functional |  | TC_06 | User is logged in | Clicking profile icon should show options | Click on the profile icon | None | Options like Logout should be visible | Options like Logout should be visible | Pass | As expected
| Security |  | TC_07 | User is logged out | Accessing the page without login | Try opening NoteMaster URL without logging in | None | Should redirect to login page | Should redirect to login page | Pass | As expected
| Performance |  | TC_08 | User is logged in | Measure how fast the page loads | Use browser DevTools to measure load time | None | Page should load within acceptable time (<3 sec) | Page should load within acceptable time (1.49sec) | Pass | As expected
| Responsive |  | TC_09 | Page is loaded | Ensure UI elements adjust properly | Resize browser window to mobile view | None | UI should adjust properly without breaking layout | UI should not adjust properly without breaking layout | Fail | Need to fix
| Accessibility |  | TC_10 | Page is loaded | Ensure text is accessible via screen readers | Use a screen reader and navigate the page | None | Text should be read aloud properly | Text should be read aloud properly | Pass | As expected
| UI/UX |  | TC_11 | Page is loaded | Ensure colors follow accessibility guidelines | Inspect color contrast using a contrast checker | None | Text should be readable with sufficient contrast | Text should be readable with sufficient contrast | Pass | As expected
| Usability |  | TC_12 | Page is loaded | Check if buttons change appearance on hover | Hover over "Write Notes" and "Create Notebook" | None | Buttons should show hover effect | Buttons should show hover effect | Pass | As expected
| UI/UX |  | TC_13 | Page is loaded | Check if button text is easy to understand | Read button labels | None | Button labels should be clear | Button labels should be clear | Pass | As expected
| Functional |  | TC_14 | "Write Notes" is clicked | Check if a new note can be created successfully | 1. Click "Write Notes" 2. Type content 3. Save | Sample note text | Note should be created and saved | Note should be created and saved | Pass | As expected
|  |  | TC_15 | "Create Notebook" is clicked | Ensure new notebook is created successfully | 1. Click "Create Notebook" 2. Enter name 3. Save | Sample notebook name | Notebook should be created successfully | Notebook should be created successfully | Pass | As expected
| Compatibility |  | TC_16 | Page is loaded | Ensure the page works in different browsers | Open in Chrome, Firefox, Edge | None | Page should function correctly in all browsers | Page should function correctly in all browsers | Pass | As expected

## Profile Page
Test Cases for Signup
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS_04 | Functional | c | TC_01 | User is logged in | Ensure clicking profile name opens the dropdown | Launch the app. → Select the section where the user’s welcome message is shown. | None | Dropdown should appear with options | Dropdown should appear with options | Pass | As expected
|  |  | TC_02 | Dropdown is open | Ensure clicking outside the dropdown closes it | • Click the profile avatar. → Tap outside the dropdown to make sure it closes automatically. | None | Dropdown should close | Dropdown should close | Pass | As expected
|  |  | TC_03 | User is logged in | Clicking "Profile" should open the profile page | • Access the profile dropdown. → Click on “Profile” from the list of available options. | None | User should be redirected to the profile page | User should be redirected to the profile page | Pass | As expected
|  |  | TC_04 | User is logged in | Clicking "Todo" should open the Todo page | • Open the profile menu. → Select the “Todo” item. | None | User should be redirected to the Todo page | User should be redirected to the Todo page | Pass | As expected
|  |  | TC_05 | User is logged in | Clicking "Dashboard" should open the dashboard | • Enter the dashboard section. → Click on “Dashboard” within the dropdown. | None | User should be redirected to the Dashboard | User should be redirected to the Dashboard | Pass | As expected
|  |  | TC_06 | User is logged in | Clicking "All Notes" should open the Notes section | Navigate to user content. → Choose “All Notes” from the profile menu. | None | User should be redirected to the All Notes page | User should be redirected to the All Notes page | Pass | As expected
|  |  | TC_07 | User is logged in | Clicking "All Notebooks" should open the notebooks page | Expand the profile dropdown. → Then click on “All Notebooks | None | User should be redirected to the All Notebooks page | User should be redirected to the All Notebooks page | Pass | As expected
|  |  | TC_08 | User is logged in | Clicking "Logout" should log out the user | • Open the user settings menu. → Log out by selecting “Logout”. | None | User should be logged out and redirected to login page | User should be logged out and redirected to login page | Pass | As expected
| UI/UX |  | TC_09 | User is logged in | Ensure the dropdown is properly aligned | • Open the dropdown from the profile. → Check that everything is properly aligned and the layout looks correct. | None | Dropdown should be aligned properly | Dropdown should be aligned properly | Pass | As expected
|  |  | TC_10 | User is logged in | Ensure text is clearly readable | Check the dropdown content. → Make sure text is easy to read and color contrast is accessible. | None | Text should be clear and readable | Text should be clear and readable | Pass | As expected
|  |  | TC_11 | User is logged in | Ensure dropdown options are properly spaced | View the full dropdown menu. → Inspect the spacing, padding, and margins between the elements. | None | Spacing should be uniform | Spacing should be uniform | Pass | As expected
| Accessibility |  | TC_12 | User is logged in | Ensure dropdown can be accessed via keyboard | Use the keyboard to explore options. → Navigate using Tab, and select using Enter. | None | Dropdown should be navigable with keyboard | Dropdown should not be navigable with keyboard | Fail | need to fix
|  |  | TC_13 | User is logged in | Ensure dropdown is readable by screen readers | Use the keyboard to explore options. → Navigate using Tab, and select using Enter. | None | Screen reader should read the menu items | Screen reader should read the menu items | Pass | As expected
| Usability |  | TC_14 | User is logged in | Ensure hovering over options changes their appearance | • Mouse over each dropdown item. → Verify hover states work and highlight correctly. | None | Options should highlight on hover | Options should highlight on hover | Pass | As expected
| Functional |  | TC_15 | Slow internet connection | Ensure dropdown is accessible even with slow loading | Simulate low network speed. → Attempt to open the dropdown and watch for loading issues. | None | Dropdown should appear normally | Dropdown should appear normally | Pass | As expected
|  |  | TC_16 | User is logged in | Ensure rapid clicks don’t close dropdown unexpectedly | • Quickly click the profile icon multiple times. → Ensure there’s no visual glitch or duplication of the dropdown. | None | Dropdown should remain stable | Dropdown should remain stable | Pass | As expected
| Security |  | TC_17 | User is logged out | Ensure dropdown doesn’t appear when not logged in | Run the app without logging in. → Try opening the profile menu to confirm it is blocked or hidden. | None | Dropdown should not be accessible | Dropdown should not be accessible | Pass | As expected
| Functional |  | TC_18 | User is logged into the system | Ensure that the profile details (name, email, role) are correctly displayed | • Log in with valid user data. → Visit the profile and check if the name, email, and role display properly. | Valid user credentials | The correct name, email, and role should be displayed on the profile page | To be filled after execution | Pass | As expected
|  |  | TC_19 | User is on the profile page | Ensure the user can upload a profile picture and it displays correctly | • Click on the user’s profile photo. → Upload a JPEG/PNG image and make sure it updates correctly. | A valid image file (JPEG, PNG) | The uploaded image should be displayed as the profile picture | The uploaded image should be displayed as the profile picture | Pass | As expected
|  |  | TC_20 | User is logged in and on the profile page | Ensure clicking "Edit Profile" redirects the user to the edit profile page | Click the "Edit Profile" button. → Verify that the user is taken to the profile editing screen. | None | The user should be redirected to the edit profile page | To be filled after execution | Pass | As expected

## To-Do
Test Cases for SignUp
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS_05 | UI Testing | Verify To-Do Page | TC_01 | Page is loaded | Ensure all elements are displayed properly | Open the To-Do list page and check if all elements (input fields, dropdowns, button, labels) are present | None | All elements should be displayed | All elements should be displayed | Pass | As expected
| Functional |  | TC_02 | Page is loaded | User should be able to add a to-do | 1. Enter text in "Write Todo" field 2. Select priority 3. Select due date 4. Click on "Add" button | Task: "Buy groceries" Priority: High Due date: 04/10/2025 | The new task should be added to the list | The new task should be added to the list | Pass | As expected
|  |  | TC_03 | Page is loaded | System should prevent empty task addition | Click the "Add" button without entering any text | None | Error message should be displayed | Error message should be displayed | Pass | As expected
|  |  | TC_04 | Page is loaded | User should be able to select different priority levels | Open the Priority dropdown and select different values | Low, Medium, High | Selected priority should be applied | Selected priority should be applied | Pass | As expected
|  |  | TC_05 | Page is loaded | User should be able to select a due date | Open the Date Picker and select a valid future date | 2025-04-15 | Selected date should be applied | Selected date should be applied | Pass | As expected
|  |  | TC_06 | Page is loaded | System should prevent past dates selection | Open the Date Picker and select a past date | 2023-03-01 | Error message should be displayed | Error message should be displayed | Pass | As expected
|  |  | TC_07 | Page is loaded | All fields should be required | Try adding a task without selecting priority or due date | Task: "Meeting with client" No priority No due date | Error message should be displayed | Error message should be displayed | Pass | As expected
|  |  | TC_08 | Page is loaded | System should prevent duplicate tasks | Add a task with the same text, priority, and date as an existing task | "Buy groceries" Priority: High Due date: 04/10/2025 | Error message should be displayed | Error message should be displayed | Pass | As expected
| Usability |  | TC_09 | Page is loaded | Page should be accessible for all users | Check if all elements have proper labels, contrast, and keyboard accessibility | None | All elements should be easily accessible | All elements should be easily accessible | Pass | As expected
| Performance |  | TC_10 | Page is loaded | Page should load properly on different devices | Open page on mobile, tablet, and desktop | Different screen sizes | Page should be responsive | Page should be responsive | Pass | As expected
| Functional |  | TC_11 | At least 1 task added | User should be able to delete a task | Add a task, then delete it | Task: "Buy milk" | Task should be removed | Task should be removed | Pass | As expected
|  |  | TC_12 | At least 1 task added | User should be able to edit a task | Add a task, click edit, modify text, save changes | Update task name | Changes should be saved | Changes should be saved | Pass | As expected
|  |  | TC_13 | At least 1 task added | User should be able to mark tasks as completed | Add a task, mark it as completed, and verify | Task: "Exercise" | Task should be marked as completed | Task should be marked as completed | Pass | As expected
|  |  | TC_14 | No tasks available | Empty list message should be displayed | Open the page when there are no tasks | None | "No todos found" message should be shown | "No todos found" message should be shown | Pass | As expected
| Compatibility |  | TC_15 | Page is loaded | System should work on different browsers | Open the page on Chrome, Firefox, Edge | None | Page should function correctly | Page should function correctly | Pass | As expected

## Write Notes
Test Cases for SignUp
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS_06 | Functional | Verify Write Notes Page | TC_01 | User is logged in | User should be able to create a new note | 1. Click on "Notes Title" field 2. Enter text 3. Start typing in the editor | Sample note text | Note should be created successfully | Note should be created successfully | Pass | As expected
|  |  | TC_02 | User has at least one saved note | User should be able to edit a saved note | 1. Select an existing note 2. Modify the text 3. Click on "Save Changes" | Modified note text | Changes should be saved successfully | Changes should be saved successfully | Pass | As expected
|  |  | TC_03 | User has at least one saved note | User should be able to delete a saved note | 1. Select a note 2. Click on delete button 3. Confirm deletion | None | Note should be deleted successfully | Note should be deleted successfully | Pass | As expected
|  |  | TC_04 | User is on the notes page | User should be able to select a notebook | 1. Click on "Choose notebook..." 2. Select a notebook | Any notebook name | Selected notebook should be assigned to the note | Selected notebook should be assigned to the note | Pass | As expected
|  |  | TC_05 | User is on the notes page | User should be able to enable/disable reminders | 1. Click on "Enable Reminders" checkbox 2. Add or remove reminders | Date and time selection | Reminders should be enabled or disabled accordingly | Reminders should be enabled or disabled accordingly | Pass | As expected
|  |  | TC_06 | User has enabled reminders | User should be able to add a reminder | 1. Click "Add Reminder" 2. Select date and time 3. Confirm selection | Date and time input | Reminder should be added successfully | Reminder should be added successfully | Pass | As expected
|  |  | TC_07 | At least one reminder is set | User should be able to delete a reminder | 1. Click on delete button next to reminder 2. Confirm deletion | None | Reminder should be deleted successfully | Reminder should be deleted successfully | Pass | As expected
| UI |  | TC_08 | User is on the notes page | UI should be correctly aligned | Visually inspect all UI elements | None | UI should be aligned properly without overlap | UI should be aligned properly without overlap | Pass | As expected
|  |  | TC_09 | User is on the notes page | Buttons should have proper styling | Inspect button styles | None | Buttons should have proper colors, fonts, and padding | Buttons should have proper colors, fonts, and padding | Pass | As expected
| Usability |  | TC_10 | User is on the notes page | The editor should be user-friendly | 1. Try editing a note 2. Test formatting options | Bold, italic, underline | Formatting should be applied correctly | Formatting should be applied correctly | Pass | As expected
|  |  | TC_11 | User has multiple notes | Navigation should be seamless | 1. Open different notes 2. Switch between them | None | Notes should open without lag | Notes should open without lag | Pass | As expected
| Performance |  | TC_12 | User is on the notes page | Editor should load within acceptable time | Open the editor and measure load time | None | Editor should load within 2 seconds | Editor should load within 2 seconds | Pass | As expected
|  |  | TC_13 | User has set a reminder | Reminders should trigger at the right time | Wait until the reminder time | None | Notification should appear at the exact time | Notification should appear at the exact time | Pass | As expected
| Security |  | TC_14 | User is logged out | Notes should not be accessible | Try accessing notes URL directly | None | Should redirect to login page | Should redirect to login page | Pass | As expected
|  |  | TC_15 | User is logged in | Notes should be encrypted or secured | Check storage method | None | Notes should be stored securely | Notes should be stored securely | Pass | As expected
| Functional |  | TC_16 | User is on the notes page | Notes should not be saved without a title | Try saving a note without a title | None | Should show a warning message | Should show a warning message | Pass | As expected
|  |  | TC_17 | User is on the notes page | Notes should not be saved if empty | Try saving an empty note | None | Should show an error message | Should show an error message | Pass | As expected
|  |  | TC_18 | User is on the notes page | Long text should be handled properly | Enter a very long text | Large text | Should not crash or truncate unexpectedly | Should not crash or truncate unexpectedly | Pass | As expected
|  |  | TC_19 | User is on the notes page | System should validate reminder date | Set a reminder for a past date | Past date | Should show a validation error | Should show a validation error | Pass | As expected
|  |  | TC_20 | User is on the notes page | The system should handle errors gracefully | Cause an unexpected error (e.g., network failure) | None | Should show an appropriate error message | Should show an appropriate error message | Pass | As expected
| Usability |  | TC_21 | User accesses the page on mobile | The interface should be responsive | Open notes page on mobile | None | UI should adjust properly | UI should adjust properly | Pass | As expected
|  |  | TC_22 | User is using keyboard shortcuts | Keyboard shortcuts should work correctly | Try common shortcuts (Ctrl+B for bold, etc.) | None | Shortcuts should apply correct formatting | Shortcuts should apply correct formatting | Pass | As expected
| Functional |  | TC_23 | User has enabled reminders | Multiple reminders should be allowed | Add multiple reminders | Multiple dates | All reminders should be added successfully | All reminders should be added successfully | Pass | As expected
|  |  | TC_24 | User has saved reminders | Reminders should not be lost after page reload | Refresh the page and check reminders | None | All reminders should be intact | All reminders should be intact | Pass | As expected
| Security |  | TC_25 | User logs out | Notes and reminders should not be accessible after logout | Logout and try accessing the page | None | Should redirect to login page | Should redirect to login page | Pass | As expected

## Create Notebook
Test Cases for SignUp
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS_07 | Functional | Verify Create Notebook Page | TC_01 | User is on the "Create Notebook" screen | Ensure a notebook is created when a valid title is entered | 1. Enter a valid notebook title 2. Click "Submit" | "My Notebook" | Notebook should be created successfully and saved | Notebook should be created successfully and saved | Pass | As expected
TS_08 |  |  | TC_02 | User is on the "Create Notebook" screen | Check if the system prevents creating a notebook without a title | 1. Leave the title field blank 2. Click "Submit" | "" (Blank) | Error message should be displayed | Error message should be displayed | Pass | As expected
TS_09 | UI/UX |  | TC_03 | User is on the "Create Notebook" screen | Ensure all UI elements are properly displayed | 1. Check if the title input field, "Close" and "Submit" buttons are visible | None | All UI elements should be aligned and visible | All UI elements should be aligned and visible | Pass | As expected
TS_10 | Usability |  | TC_04 | User is on the "Create Notebook" screen | Check if the "Close" button properly closes the form | 1. Click "Close" | None | The form should be closed without saving any data | The form should be closed without saving any data | Pass | As expected
TS_11 | Functional |  | TC_05 | User is on the "Create Notebook" screen | Check if the system allows only a specific character limit | 1. Enter a title with 255 characters (or limit defined by the system) 2. Click "Submit" | 255 characters | Notebook should be created successfully | Notebook should be created successfully | Pass | As expected
TS_13 |  |  | TC_06 | User is on the "Create Notebook" screen | Ensure the system handles duplicate notebook titles correctly | 1. Create a notebook with title "Work Notes" 2. Try to create another with the same title | "Work Notes" | System should either allow it or show an error | System should either allow it or show an error | Pass | As expected